## Objectives
Review |  | Objectives | Phase applicability M: mandatory / O: optional / Blank: excluded
Name | Acronym |  | Definition | Technology | Product | Demonstration
Baseline Design Review | BDR | 1. Finalisation of User Needs and User Requirements, definition of System Requirments - Release of the Design Definition and Verification Plan (DDVP) and Requirements Document (RD). | M | M | M | M
|  | 2. Detailed definition of Pilot Service, including KPIs and users role - Release of the Pilot Utilisation Plan (PilUP). |  |  | O | M
|  | 3. Release of Project Web Page (PWP). | M | M | M | M
Critical Design Review | CDR | 1. Approve the final design and associated trade-off processes. | O | O | M | O
|  | 2. Finalisation of System Requirments - Finalisation of Requirments Document (RD) . |  | O | M | M
|  | 3. Finalisation of the System and Service Architecture - Release of System and Services Architecture (SSA). | O | O | M | M
|  | 4. Release of the Design Definition and Verification Plan (DDVP). | O | O | M | M
|  | 5. Definition of Verification Approach - First release of System Verification Document (SVD). |  | O | M | M
Factory Acceptance Test | FAT | 1. Finalisation of Test Plan and Procedures |  | O | M | M
|  | 2. Review of outcomes of the verification performed internally by contractor - Release of System Verification Document (SVD). |  | O | M | M
|  | 3. Perform a subset of Verification Tests witnessed by ESA. |  | O | M | M
|  | 4. Verify the acceptability of any non-conformances. |  |  | M | M
|  | 5. Certify successful completion of development/integration stage. |  | O | M | M
on-Site Acceptance Test | SAT | 1. Review of outcomes of the verification perfomed internally by contractor on the Pilot Sites - Update of System Verification Document (SVD). |  |  |  | M
|  | 2. Perform a subset of Verification Tests witnessed by ESA. |  |  |  | M
|  | 3. Ensure pilot users agreement and support concerning pilot execution with participation of pilot users. |  |  |  | M
|  | 4. Finalise description of Pilot Activities incl. procedures and tools for pilot outocomes and KPIs - Update of Pilot Utilisation Plan (PilUP). |  |  |  | M
|  | 5. Finalise the objectives of utilisation in the pilot activities - Update of Pilot Utilisation Summary Report (POSR). |  |  |  | M
|  | 6. Kick off the pilot activities with the involvement of pilot users. |  |  |  | M
Phase Completion Review | PCR | 1. Present a summary of the outcome of the development phase, including conclusions and recommendations. | M | M | M | M
|  | 2. Present the results of the verification and validation, as applicable |  | M | M | M
|  | 3. Present an outline of future development and commercial exploitation strategies. | M | M | M | M
|  | 4. Release the Final Report (FR) and the othe relements of the Final Data Package (FDP). | M | M | M | M
Final Review | FR | 1. Present a summary of the outcome of the development, including conclusions and recommendations. | M | M | M | M
|  | 2. Present a summary of the outcomes of the pilot operations, including the conclusions and recommendations gathered from the pilot users and other stakeholders involved in the project and the expected impacts in the commercial roll out phase. - Release of the Pilot Utilisation Plan (PilUP). |  |  |  | M
|  | 3. Release of the Summary & Achievements (S&A). | O | M | M | M
|  | 4. Present an outline of future development and commercial exploitation strategies. | M | M | M | M
|  | 5. Release the Final Report (FR) and the othe relements of the Final Data Package (FDP). | M | M | M | M
|  | 6. Review status of the Final Check List and agree/record actions to finalise the contract. | M | M | M | M

## Deliverables
Document |  |  | Phase applicability M: mandatory R: recommended |  |  |  | Review Data Package M: mandatory R: recommended | [5 empty] | Document definition |  | Comments
Reference | Title | Acronym | Definition | Technology | Product | Demonstration | BDR | CDR | FAT | SAT | PCR | FR | Reference | Applicability M: mandatory R: recommended
Management
A.MG1 | Business Plan | BP | M | M | M | M | M | M | M | M | M | M | Part 2 requirements | M
A.MG2 | Monthly Progress Report | MPR | M | M | M | M | M / Monthly | [5 empty] | Template in hyperlink | M
A.MG3 | Project Bar Chart | PBC | M | M | M | M | M / At each progress meeting | [5 empty] | Part 5B, Req. 3.3 | M
A.MG4 | Minutes of Meeting | MoM | M | M | M | M | M / For each review or meeting | [5 empty] | Part 5A, Req. 3.2 and 3.3 | M | Template for MoM of Negotiation Meeting in hyperlink
A.MG5 | Risk Register | RR | M | M | M | M | M / Monthly and at each progress meeting | [5 empty] | ECSS-M-ST-80C, Annex D | R
A.MG6 | Document List | DL | M | M | M | M | M | M | M | M | M | M | Self descriptive |  | List of all documents produced in the frame of the contract
A.MG7 | Final Report(1) | FR | M | M | M | M |  |  |  |  | M | M | Part 5C, Annex | M
A.MG8 | Final Data Package | FDP | M | M | M | M |  |  |  |  | M | M | Part 5C, Annex | M
A.MG9 | Justification for non-continuation |  | M | M | [7 empty] | M | Part 5C, Req. 4.8 and 4.9 | M | If applicable
A.MG10 | Project Web Page(1) | PWB | M | M | M | M | M | M | M | M | M | M | Template in hyperlink | M
A.MG11 | Digital Media(1) | DM |  | M | M | M | [5 empty] | M | Part 5C, Annex | M
A.MG12 | Contract Inventory | CI |  | M | M | M |  |  |  |  | M | M | See contract |  | List of all items produced under the Contract with an individual or batch value exceeding 10k€
A.MG13 | Contract Outcome Data | COD |  | R | M | M |  |  |  |  | R | M | Part 5C, Annex | M | Template in hyperlink
A.MG14 | Summary and Achievements | S&A |  | R | M | M |  |  |  |  | R | M | Part 5C, Annex | M
A.MG19 | Schedule for follow-on Phase(s) |  | M | M | M | M |  |  |  |  | M
A.MG20 | Review and Deliverable Plan for follow-on Phase(s) |  | M | M | M | M |  |  |  |  | M
A.MG21 | Costings for follow-on phase(s) |  | M | M | M | M |  |  |  |  | M
Engineering
A.EN1 | Design Definition and Verification Plan | DDVP | R | M | M | M | M | M | R | R | M | M | Part 3B and 3C | M
A.EN2 | Requirements Document | RD | M | R | M | M | M | M |  |  | M | M | Part 5C, Annex | M
A.EN3 | System and Service Architecture | SSA | M | R | M | M | M | M | R | R | M | M | Part 5C, Annex | M
A.EN4 | User Manual | UM |  | R | M | M |  | R | R | M | M | M | Self descriptive
Verification
A.VE1 | System Verification Document | SVD |  | R | M | M | R | M | M | M | M | M | Part 5C, Annex
A.VE2 | Acceptance Test Plan (as part of SVD). | ATPL |  | R | M | M | R | M | M | M | M | M
A.VE3 | Acceptance Test Procedure(as part of SVD). | ATP |  | R | M | M | R | M | M | M | M | M
A.VE4 | Acceptance Test Report (as part of SVD). | ATR |  | R | M | M |  |  | M | M | M | M
Validation
A.VA1 | Pilot Utilisation Plan | PilUP |  |  |  | M | M | R | M | M | M | M | Part 5C, Annex | M
A.VA2 | Pilot Operations Summary Report | POSR |  |  |  | M | R | R | R | M | M | M | Part 5C, Annex | M | Template in hyperlink
Weekly from pilot installation
Software (if applicable)
A.SW1 | Software Reuse File | SRF |  | R | M | M | R | M |  |  | M | M | Part 5C, Annex | M
A.SW2 | Software User Manual | SUM |  | R | M | M |  |  | R | M | M | M | Self descriptive
(1) intended for general publication and will NOT be treated in confidence