## Review objectives
Review |  | Objectives | Phase applicability M: mandatory / O: optional / Blank: excluded
Name | Acronym |  | Definition | Technology | Scylight Demonstration | Product
Mid Term Review | MTR | 1. Release of the preliminary technical requirements specification. | M
|  | 2. Preliminary concept(s) and technical solutions, including model philosophy and verification approach, to be carried forward. | M
Requirements Review | RR | 1. Release the updated technical requirements specification. |  | O
|  | 2. Assess the preliminary design definition. |  | O
|  | 3. Release the preliminary verification plan. |  | O
Preliminary Design Review | PDR | 1. Approve the technical requirements specification at all levels. |  | M |  | O
|  | 2. Verify the preliminary design of the selected concept and technical solutions against all requirements (including interfaces). |  | M |  | O
|  | 3. Close all technical trade-offs. |  | M |  | O
|  | 4. Demonstrate the feasibility of the selected concept. |  | M |  | O
|  | 5. Identify critical points and propose risk mitigation actions. |  | M |  | O
|  | 6. Release final management, engineering and product assurance plans (as applicable) |  | M |  | O
|  | 7. Establish the verification plan (including draft test plans). |  | M |  | O
Critical Design Review | CDR | 1. Approve the final design. |  |  | M | M
|  | 2. Assess, through review, analysis or test results, the compliance status with the technical requirements specification (including interfaces). |  |  | M | M
|  | 3. Release production manufacturing, assembly and testing documents. |  |  | M | M
|  | 4. Release the user manual. |  |  | M | M
|  | 5. Approve the verification test plan. |  |  | M | M
Test Readiness Review | TRR | 1. Verify test documentation availability and suitability, including: (a) approved AIT Plan, (b) approved test specification, (d) test procedures , (e) test schedule, |  | O | O | M
|  | 2. Verify that the tested item(s) is(are) built to the required standard. |  | O | O | M
|  | 4. Check that the item is in the correct test configuration. |  | O | O | M
|  | 5. Verify the acceptability of all non-conformances, waivers and deviations. |  | O | O | M
|  | 6. Confirm that test facilities and personnel are available and adequate. |  | O | O | M
Factory Acceptance Test | FAT | 1. Review of outcomes of the verification performed internally by contractor |  | O | M | M
|  | 2. Perform a subset of Verification Tests witnessed by ESA. |  | O | M | M
|  | 3. Verify the acceptability of any non-conformances. |  | O | M | M
4. Certify successful completion of development/integration stage.
Phase Completion Review | PCR | 1. Present a summary of the outcome of the development phase, including conclusions and recommendations. | M | M | M | M
|  | 2. Propose an outline of future product development strategies. | M | M | M | M
|  | 3. Present the test or operational data gathered during the phase | O | M | M | M
Final Review | FR | 1. Present a summary of the outcome of the development, including conclusions and recommendations. | M | M | M | M
|  | 2. Propose an outline of future product development strategies. | M | M | M | M
|  | 3. Present the qualification test results (if no qualification review has been held previously). |  |  |  | M
|  | 4. Provide an estimation of the socioeconomic impact of the product development and of the subsequent commercialisation of the product |  |  | M | M
|  | 5. Present the operational data gathered during the first year of operation of the product. |  |  | M
|  | 6. Compare the operational data with performance predictions, including a trend analysis. |  |  | M
|  | 7. List and assess any anomaly observed during operation. |  |  | M

## Deliverables
Document |  |  | Phase applicability M: mandatory R: recommended |  |  |  | Review Data Package M: mandatory R: recommended | [7 empty] | Document definition |  | Comments
Reference | Title | Acronym | Definition | Technology | SycLight Demonstration | Product | MTR | RR | PDR | CDR | TRR | FAT | PCR | FR | Reference | Applicability M: mandatory R: recommended
Management
G.MG1 | Project Management Plan | PMP | M | M | M | M | [8 empty] | Part 5A, Req. 1.1 | M | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended FR
[15 empty] | ECSS-M-ST-10, Annex A | R
G.MG2 | Configuration and Documentation Management Plan | CMDP | R | R | R | R | [8 empty] | Part 5A, Req. 2.2 and 2.3 | M | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended PDR
[15 empty] | ECSS-M-ST-40, Annex A | R
G.MG3 | Risk Management Plan | RMP | R | R | R | R | [8 empty] | ECSS-M-ST-80, Annex B | R | May be merged with G.MG1 in one single document. | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR
G.MG4 | Review Procedure |  | R | R | R | R | Review Data Package M: mandatory R: recommended MTR: R / At each review | ECSS-M-ST-10-01, Annex A | R
G.MG5 | Business Potential | BP | M | M | M | M | [8 empty] | Part 2 | M | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
G.MG6 | Monthly Progress Report | MPR | M | M | M | M | Review Data Package M: mandatory R: recommended MTR: M / Monthly | Template in hyperlink | M | Also see Part 5A, Req. 3.1-3.3 and part 5C Annex
G.MG7 | Schedule Bar Chart | SBC | M | M | M | M | Review Data Package M: mandatory R: recommended MTR: M / Monthly and at each progress meeting | Part 5B, Req. 3.3 | M | May be merged with G.MG6 in one single document.
[15 empty] | ECSS-M-ST-60, Annex B. | R
G.MG8 | Minutes of Meeting | MoM | M | M | M | M | Review Data Package M: mandatory R: recommended MTR: M / For each review or meeting | Part 5A, Req. 3.2 and 3.3 | M
G.MG9 | Risk Register | RR | M | M | M | M | Review Data Package M: mandatory R: recommended MTR: M / Monthly and at each progress meeting | ECSS-M-ST-80C, Annex D | R
G.MG10 | Document List | DL | M | M | M | M | [8 empty] | Self descriptive |  | List of all documents produced in the frame of the contract | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended FR
G.MG11 | Final Report(1) | FR | M | M | M | M | [8 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
G.MG12 | Final Data Package | FDP | M | M | M | M | [8 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
G.MG13 | Justification for non-continuation |  | M | M | M | [9 empty] | Part 5C, Req. 4.8 and 4.9 | M | If applicable. | bar: Review Data Package M: mandatory R: recommended FR
G.MG14 | Project Web Page(1) | PWP | M | M | M | M | [8 empty] | Template in hyperlink | M | Also see Part 5A, Req. 3.5 – 3.8 | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended FR
G.MG15 | High resolution image(1) |  | M | M | M | M | [8 empty] | Part 5C, Annex | M | Shall be delivered for each Development Phase during the last milestone review meeting of that Phase. | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
G.MG16 | Activity Summary Description(1) | ASD | M | M | M | M | [8 empty] | Part 5C, Annex | M | Shall be delivered for each Development Phase during the last milestone review meeting of that Phase. | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
G.MG17 | Socio-economic Impact Questionnaire | SIQ |  |  | M | M | [8 empty] | Part 5C, Annex | M | Template in hyperlink | bar: Review Data Package M: mandatory R: recommended FR
G.MG18 | Contract Inventory |  | M | M | M | M | [8 empty] | See Contract | R | List of all items produced under the Contract with an individual or batch value exceeding 10k€. See contract | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
Engineering
G.EN1 | Design, Development and Verification Plan / Product Development Plan |  | M | M | M | M | [8 empty] | Parts 3B and 3C | M | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
G.EN2 | Technical Requirements Specification / Product Specification |  | M | M | M | M | [8 empty] | Part 3A | M | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended TRR
[15 empty] | ECSS-E-ST-10-06, Annex A | R
G.EN3 | Requirements Traceability Matrix | RTM | R | R | M | M | [8 empty] | ECSS-E-ST-10, Annex N | R | If applicable. May be merged with G.EN2 in one single document. | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR
G.EN4 | Verification Control Document | VCD | R | R | R | R | [8 empty] | ECSS-E-ST-10-02, Annex B | R | bar: Review Data Package M: mandatory R: recommended MTR; Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR
G.EN5 | Compliance Matrix to Technical Specification |  |  | M | M | M | [8 empty] | Self descriptive |  | May be merged with G.EN2 in one single document. | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR
G.EN6 | Design Verification Compliance Matrix | DVCM |  | M | M | M | [8 empty] | ECSS-E-ST-10-02, Annex B |  | May be merged with G.EN2 in one single document. | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR
G.EN7 | Specification tree |  | R | R | R | R | [8 empty] | ECSS-E-ST-10, Annex J | R | If applicable. | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR
G.EN8 | Design Definition File | DDF | R | M | M | M | [8 empty] | ECSS-E-ST-10, Annex G | R | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR
G.EN9 | Design Justification File | DJF | R | M | M | M | [8 empty] | ECSS-E-ST-10, Annex K | R | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR
G.EN10 | Part drawings |  |  | R | R | M | [8 empty] | Self descriptive | R | May be available for on-site review only. | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR
G.EN11 | Assembly drawings |  |  | R | R | M | [8 empty] | Self descriptive | R | May be available for on-site review only. | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR
G.EN12 | Interface Control Document | ICD |  | R | M | M | [8 empty] | ECSS-E-ST-10-24, Annex C | R | bar: Review Data Package M: mandatory R: recommended RR to Review Data Package M: mandatory R: recommended CDR
G.EN13 | User Manual | UM |  |  | M | R | [8 empty] | ECSS-E-ST-10, Annex P | R | bar: Review Data Package M: mandatory R: recommended CDR
G.EN14 | Trade-Off Report | TOR | R | R | R | [9 empty] | ECSS-E-ST-10, Annex L | R | If applicable | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended PDR
G.EN15 | Performance Analyses |  | R | R | R | M | [8 empty] | ECSS-E-ST-10, Annex Q | R | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR
G.EN16 | Technical Description |  | R | R | R | R | [8 empty] | Self descriptive | R | bar: Review Data Package M: mandatory R: recommended RR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended FR
Testing
G.TE1 | Assembly, Integration and Test Plan | AITP |  | R | R | R | [8 empty] | ECSS-E-ST-10-03, Annex A | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR
G.TE2 | Test Specification | TSPE |  | M | R | M | [8 empty] | ECSS-E-ST-10-03, Annex B | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR
G.TE3 | Test Procedure | TPRO |  | R | R | M | [8 empty] | ECSS-E-ST-10-03, Annex C | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR
G.TE4 | Test Report | TRPT |  | M | M | M | [8 empty] | ECSS-E-ST-10-02, Annex C | R | bar: Review Data Package M: mandatory R: recommended FAT to Review Data Package M: mandatory R: recommended FR
G.TE5 | AIT report | AITR |  |  | R | R | [8 empty] | ECSS-E-ST-10-02, Annex C | R | bar: Review Data Package M: mandatory R: recommended FAT
Product Assurance
G.PA1 | Product Assurance Plan / Quality Plan | PAP |  | R | R | R | [8 empty] | ECSS-Q-ST-10, Annex A | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR
G.PA2 | Quality Assurance Plan | QAP |  | R | R | M | [8 empty] | ECSS-Q-ST-20, Annex A | R | May be merged with G.PA1 in one single document | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR
G.PA3 | Critical Item List | CIL |  | M | R | M | [8 empty] | ECSS-Q-ST-10-04, Annex A | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR
G.PA4 | Configuration Item Data List | CIDL |  | R | R | M | [8 empty] | ECSS-M-ST-40, Annex C | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR
G.PA5 | Product Data Sheet |  |  | M | R | M | [8 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
G.PA6 | Handling, Packing, Storage, and Transporttion |  |  |  | M | M | [8 empty] | Self descriptive | M | bar: Review Data Package M: mandatory R: recommended FAT; Review Data Package M: mandatory R: recommended FR
Software (if applicable)
G.SW1 | Software Configuration File | SCF |  | R | R | R | [8 empty] | ECSS-M-ST-40, Annex E | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR
G.SW2 | Software Requirements Specification | SRS | R | R | R | R | [8 empty] | ECSS-E-ST-40, Annex D | R | bar: Review Data Package M: mandatory R: recommended MTR; Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR
G.SW3 | Software Interface Control Document | SICD |  | R | R | R | [8 empty] | ECSS-E-ST-40, Annex E | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR
G.SW4 | Software Design Document | SDD | R | R | R | R | [8 empty] | ECSS-E-ST-40, Annex F | R | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR
G.SW5 | Software Release Document | SrelD |  |  | R | R | [8 empty] | ECSS-E-ST-40, Annex G | R | bar: Review Data Package M: mandatory R: recommended TRR
G.SW6 | Software User Manual | SUM |  |  | R | R | [8 empty] | ECSS-E-ST-40, Annex H | R | bar: Review Data Package M: mandatory R: recommended CDR to Review Data Package M: mandatory R: recommended TRR
G.SW7 | Software Verification Plan | SVerP |  | R | R | R | [8 empty] | ECSS-E-ST-40, Annex I | R | bar: Review Data Package M: mandatory R: recommended RR to Review Data Package M: mandatory R: recommended TRR
G.SW8 | Software Verification Report | SVR |  |  | R | R | [8 empty] | ECSS-E-ST-40, Annex M | R | bar: Review Data Package M: mandatory R: recommended FAT
G.SW9 | Software Development Plan | SDP | R | R | R | R | [8 empty] | ECSS-E-ST-40, Annex O | R | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR
G.SW10 | Software Configuration Management Plan |  |  | R | R | R | [8 empty] | ECSS-M-ST-40, Annex A | R | bar: Review Data Package M: mandatory R: recommended RR to Review Data Package M: mandatory R: recommended CDR
G.SW11 | Software reuse file |  |  | R | R | R | [8 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR
[15 empty] | ECSS-E-ST-40, Annex N | R
G.SW12 | Software license file |  |  |  | M | R | [8 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended CDR to Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
(1) intended for general publication and will NOT be treated in confidence