## Objectives
Review |  | Objectives | Phase applicability M: mandatory / O: optional / Blank: excluded
Name | Acronym |  | Definition | Technology | Product | Demonstration
Mid Term Review | MTR | 1. Release of the preliminary technical requirements specification. | M
|  | 2. Preliminary concept(s) and technical solutions, including model philosophy and verification approach, to be carried forward. | M
Requirements Review | RR | 1. Release the updated technical requirements specification. |  | O
|  | 2. Assess the preliminary design definition. |  | O
|  | 3. Release the preliminary verification plan. |  | O
Preliminary Design Review | PDR | 1. Approve the technical requirements specification at all levels. |  | M | O
|  | 2. Verify the preliminary design of the selected concept and technical solutions against all requirements (including interfaces). |  | M | O
|  | 3. Close all technical trade-offs. |  | M | O
|  | 4. Demonstrate the feasibility of the selected concept. |  | M | O
|  | 5. Identify critical points and propose risk mitigation actions. |  | M | O
|  | 6. Release final management, engineering and product assurance plans. |  | M | O
|  | 7. Establish the verification plan (including draft test plans). |  | M | O
Critical Design Review | CDR | 1. Approve the final design. |  |  | M | O
|  | 2. Assess, through review, analysis or test results, the compliance status with the technical requirements specification (including interfaces). |  |  | M | O
|  | 3. Assess the qualification and validation status of the critical processes. |  |  | M | O
|  | 4. Release production manufacturing, assembly and testing documents. |  |  | M | O
|  | 5. Release the user manual. |  |  | M | O
|  | 6. Approve the qualification test plan. |  |  | M | O
|  | 7. Review the qualification test specification |  |  | M | O
Test Readiness Review | TRR | 1. Verify test documentation availability and suitability, including: (a) approved AITP, (b) approved test specification, (c) test predictions (when relevant), (d) test procedures (including contingency and emergency procedures), (e) test schedule, and (f) acceptance data package of lower level items (if applicable). |  | O | M | O
|  | 2. Verify that the tested item(s) is(are) built to the required standard. |  | O | M | O
|  | 3. Check that the item is in the correct test configuration. |  | O | M | O
|  | 4. Verify the acceptability of all non-conformances, waivers and deviations. |  | O | M | O
|  | 5. Confirm that test facilities and personnel are available and adequate. |  | O | M | O
Test Review Board | TRB | 1. Review the test report. |  | O | M | O
|  | 2. Examine compliance with the test specification. |  | O | M | O
|  | 3. List and examine non-conformances. |  | O | M | O
|  | 4. Assess the status of test objectives. |  | O | M | O
Equipment Qualification Status Review | EQSR | 1. Review the equipment's design and configuration. |  |  |  | M
|  | 2. Establish the qualification status of the equipment for a given application through the review of: a. CDR documentation for existing design (category A and B); technical presentation and any supporting documents otherwise, b. all parts, materials and processes used, c. qualification test results. |  |  |  | M
|  | 3. Verify its compatibility with the technical specification. |  |  |  | M
|  | 4. Establish the development approach and design reviews that are required. |  |  |  | M
|  | 5. Verify the adequacy of acceptance test plan and procedures for the flight hardware |  |  |  | M
Acceptance Review | AR | 1. Confirm that the product conforms to the contractual requirements and to an approved design configuration. |  |  |  | M
|  | 2. Confirm that the product is free of workmanship errors and is ready for subsequent operational use. |  |  |  | M
|  | 3. Verify the completeness of the Acceptance/End Item Data Package (ADP or EIDP). |  |  |  | M
|  | 4. Verify the acceptability of all waivers and deviations. |  |  |  | M
Commissioning Results Review | CRR | 1. Review the commissioning test results relating to the performance of operational unit. |  |  |  | M
|  | 2. Compare the commissioning test results with the corresponding performance predictions. |  |  |  | M
|  | 3. Present and assess any anomaly observed during commissioning of the operational unit. |  |  |  | M
Phase Completion Review | PCR | 1. Present a summary of the outcome of the development phase, including conclusions and recommendations. | M | M | M | M
|  | 2. Propose an outline of future product development strategies. | M | M | M | M
|  | 3. Present the test or operational data gathered during the phase | O | M | M | M
Final Review | FR | 1. Present a summary of the outcome of the development, including conclusions and recommendations. | M | M | M | M
|  | 2. Propose an outline of future product development strategies. | M | M | M | M
|  | 3. Present the qualification test results (if no qualification review has been held previously). |  |  | M
|  | 4. Provide an estimation of the socioeconomic impact of the product development and of the subsequent commercialisation of the product |  |  | M | M
|  | 5. Present the operational data gathered during the first year of operation of the product. |  |  |  | M
|  | 6. Compare the operational data with performance predictions, including a trend analysis. |  |  |  | M
|  | 7. List and assess any anomaly observed during operation. |  |  |  | M
Qualification Review | QR | 1. Present the qualification test results (TRB objectives shall apply). |  |  | O | O
|  | 2. Confirm that the verification process has demonstrated that the design complies with the technical requirements specification. |  |  | O | O
|  | 3. Verify the acceptability of all waivers and deviations. |  |  |  | O
Manufacturing Readiness Review | MRR | 1. Review manufacturing, assembly, inspection and test documentation. |  |  | O | O
|  | 2. For flight hardware, identify differences with the qualification model (definition, fabrication, test) and evaluate the related impact. |  |  |  | O
|  | 3. Assess the validation status of manufacturing processes, with particular emphasis on critical processes. |  |  | O | O
|  | 4. Review the dispositions for risk reduction into the manufacturing, assembly, integration, inspection and test procedures |  |  | O | O
|  | 5. Confirm the availability of required production resources (personnel and tools) |  |  | O | O
|  | 6. Confirm the availability and compliance of parts, mechanical parts and materials. |  |  | O | O
|  | 7. Assess the cleanliness of facilities with respect to the required levels. |  |  | O | O

## Deliverables
Document |  |  | Phase applicability M: mandatory R: recommended |  |  |  | Review Data Package M: mandatory R: recommended | [12 empty] | Document definition |  | Comments
Reference | Title | Acronym | Definition | Technology | Product | Demonstration | MTR | RR | PDR | CDR | TRR | TRB | EQSR | AR | CRR | PCR | FR | QR | MRR | Reference | Applicability M: mandatory R: recommended
Management
S.MG1 | Project Management Plan | PMP | M | M | M | M | [13 empty] | Part 5A, Req. 1.1 | M | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended FR
[20 empty] | ECSS-M-ST-10C, Annex A | R
S.MG2 | Configuration and Documentation Management Plan | CMDP | R | R | R | R | [13 empty] | Part 5A, Req. 2.2 and 2.3 | M | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended PDR; Review Data Package M: mandatory R: recommended EQSR
[20 empty] | ECSS-M-ST-40C, Annex A | R
S.MG3 | Risk Management Plan | RMP | R | R | R | R | [13 empty] | ECSS-M-ST-80C, Annex B | R | May be merged with S.MG1 in one single document. | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR
S.MG4 | Review Procedure |  | R | R | R | R | Review Data Package M: mandatory R: recommended MTR: R / At each review | ECSS-M-ST-10-01, Annex A | R
S.MG5 | Business Plan | BP | M | M | M | M | [13 empty] | Part 2 | M | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended QR
S.MG6 | Monthly Progress Report | MPR | M | M | M | M | Review Data Package M: mandatory R: recommended MTR: M / Monthly | Template in hyperlink | M | Also see Part 5A, Req. 3.1 – 3.3
S.MG7 | Schedule Bar Chart | SBC | M | M | M | M | Review Data Package M: mandatory R: recommended MTR: M / Monthly and at each progress meeting | Part 5B, Req. 3.3 and 5.6 | M | May be merged with S.MG6 in one single document.
[20 empty] | ECSS-M-ST-60C, Annex B | R
S.MG8 | Minutes of Meeting | MoM | M | M | M | M | Review Data Package M: mandatory R: recommended MTR: M / For each review or meeting | Part 5A, Req. 3.2 and 3.3 | M
S.MG9 | Risk Register | RR | M | M | M | M | Review Data Package M: mandatory R: recommended MTR: M / Monthly and at each progress meeting | ECSS-M-ST-80C, Annex D | R
S.MG10 | Document List | DL | M | M | M | M | [13 empty] | Self descriptive |  | List of all documents produced in the frame of the contract | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended MRR
S.MG11 | Final Report(1) | FR | M | M | M | M | [13 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
S.MG12 | Final Data Package | FDP | M | M | M | M | [13 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
S.MG13 | Justification for non-continuation |  | M | M | [15 empty] | Part 5C, Req. 4.8 and 4.9 | M | If applicable. | bar: Review Data Package M: mandatory R: recommended FR
S.MG14 | Project Web Page(1) | PWP | M | M | M | M | [13 empty] | Template in hyperlink | M | Also see Part 5A, Req. 3.5 – 3.8 | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended TRB; Review Data Package M: mandatory R: recommended AR to Review Data Package M: mandatory R: recommended MRR
S.MG15 | High resolution image(1) |  | M | M | M | M | [13 empty] | Part 5C, Annex | M | Shall be delivered for each Development Phase during the last milestone review meeting of that Phase. | bar: Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
S.MG16 | Activity Summary Description(1) | ASD | M | M | M | M | [13 empty] | Part 5C, Annex | M | Shall be delivered for each Development Phase during the last milestone review meeting of that Phase. | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
S.MG17 | Socio-economic Impact Questionnaire | SEIQ |  |  | M | M | [13 empty] | Part 5C, Annex | M | Template in hyperlink | bar: Review Data Package M: mandatory R: recommended FR
S.MG18 | Contract Inventory |  | M | M | M | M | [13 empty] | ECSS-M-ST-60C, Annex I | R | List of all items produced under the Contract with an individual or batch value exceeding 10k€. | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
S.MG19 | Quarterly Status Report | QSR |  |  |  | M | Review Data Package M: mandatory R: recommended MTR: M / Quarterly | Part 5C, Annex | M | Also see Part 5A, Req. 6.1 – 6.3
Engineering
S.EN1 | Design, Development and Verification Plan / Product Development Plan |  | M | M | M | M | [13 empty] | Parts 3B and 3C | M | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended QR
S.EN2 | Technical Requirements Specification / Product Specification |  | M | M | M | M | [13 empty] | Part 3A | M | For lower levels as well, if applicable. | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
[20 empty] | ECSS-E-ST-10-06C, Annex A | R
S.EN3 | Requirements Traceability Matrix | RTM | R | R | M | M | [13 empty] | ECSS-E-ST-10C, Annex N | R | If applicable. May be merged with S.EN2 in one single document. | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.EN4 | Verification Control Document | VCD | R | R | R | R | [13 empty] | ECSS-E-ST-10-02C, Annex B | R | bar: Review Data Package M: mandatory R: recommended MTR; Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended CRR; Review Data Package M: mandatory R: recommended QR
S.EN2 | Compliance Matrix to Technical Specification |  |  | M | M | M | [13 empty] | Self descriptive |  | May be merged with S.EN2 in one single document. | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.EN3 | Design Verification Compliance Matrix | DVCM |  | M | M | M | [13 empty] | ECSS-E-ST-10-02C, Annex B | R | May be merged with S.EN2 in one single document. | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.EN4 | Specification tree |  | R | R | R | R | [13 empty] | ECSS-E-ST-10C, Annex J | R | If applicable. | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR
S.EN5 | Design Definition File | DDF | R | M | M | M | [13 empty] | ECSS-E-ST-10C, Annex G | R | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.EN6 | Design Justification File | DJF | R | M | M | M | [13 empty] | ECSS-E-ST-10C, Annex K | R | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.EN7 | Part drawings |  |  | R | M | R | [13 empty] | Self descriptive | R | May be available for on-site review only. | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR to Review Data Package M: mandatory R: recommended MRR
S.EN8 | Assembly drawings |  |  | R | M | R | [13 empty] | Self descriptive | R | May be available for on-site review only. | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR to Review Data Package M: mandatory R: recommended MRR
S.EN9 | Interface Control Document | ICD |  | R | M | M | [13 empty] | ECSS-E-ST-10-24C, Annex C | R | bar: Review Data Package M: mandatory R: recommended RR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR to Review Data Package M: mandatory R: recommended MRR
S.EN10 | User Manual | UM |  |  | R | M | [13 empty] | ECSS-E-ST-10C, Annex P | R | bar: Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.EN11 | Trade-Off Report | TOR | R | R | [15 empty] | ECSS-E-ST-10C, Annex L | R | If applicable | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended PDR
S.EN12 | Performance Analyses |  | R | R | M | R | [13 empty] | ECSS-E-ST-10C, Annex Q | R | For instance: worst-case performance, power budget, leakage, gauging, sloshing, motorization, kinematics. May be merged with S.EN9 in one single document. | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.EN13 | Environmental Analyses |  |  | R | M | R | [13 empty] | ECSS-E-ST-10C, Annex Q | R | For instance: thermal, mechanical, thermo-elastic, fatigue, fracture, EMC, ESD, venting, plume effects, corona. May be merged with S.EN9 in one single document. | bar: Review Data Package M: mandatory R: recommended RR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.EN17 | Mathematical Models |  |  |  | R | R | [13 empty] | ECSS-E-ST-31C, Annex B for thermal | R | E.g. performance, thermal, mechanical. | bar: Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
[20 empty] | ECSS-E-ST-32C, Annex A for CAD | R
[20 empty] | ECSS-E-ST-32C, Annex I for mechanical | R
[20 empty] | ECSS-E-ST-35C Annex I for propulsion | R
[20 empty] | ECSS-E-ST-60-20C, Annex A for star sensor | R
S.EN18 | Satellite level accommodation report |  |  |  |  | M | [13 empty] | Self descriptive | R | For instance: accommodation studies, design modifications performed to accommodate the innovative product, any hardware specifically required for accommodation purposes and satellite level AIT, specific activities related to the innovative product during the AIT and launch campaigns. | bar: Review Data Package M: mandatory R: recommended AR
S.EN19 | Technical Description |  | M | M | M | M | [13 empty] | Self descriptive | bar: Review Data Package M: mandatory R: recommended RR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.EN20 | Statement of compliance to the Specifications |  | R | R | M | M | [13 empty] | Self descriptive |  | Applicable only if multiple specifications are used | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended AR
S.EN21 | Mass Budget |  |  |  | M | M | [13 empty] | ECSS-E-ST-10C, Annex Q | M | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
Testing
S.TE1 | Assembly, Integration and Test Plan | AITP |  | R | R | R | [13 empty] | ECSS-E-ST-10-03C, Annex A | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.TE2 | Test Specification | TSPE |  | M | M | R | [13 empty] | ECSS-E-ST-10-03C, Annex B | R | These documents are required for Engineering Model testing, as well as for qualification and acceptance tests. Test procedures may be available for on-site review only. | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR
S.TE3 | Test Procedure | TPRO |  | R | M | R | [13 empty] | ECSS-E-ST-10-03C, Annex C | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.TE4 | Test Report | TRPT |  | M | M | M | [13 empty] | ECSS-E-ST-10-03C, Annex C | R | bar: Review Data Package M: mandatory R: recommended TRB to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended QR
S.TE5 | AIT report | AITR |  |  | R | R | [13 empty] | ECSS-E-ST-10-03C, Annex C | R | bar: Review Data Package M: mandatory R: recommended TRB; Review Data Package M: mandatory R: recommended AR
S.TE6 | Satellite AIT report |  |  |  |  | M | [13 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended AR
S.TE7 | In-Orbit Test plan |  |  |  |  | M | [13 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended AR
S.TE8 | IOT report |  |  |  |  | M | [13 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended CRR
S.TE9 | One-year in-orbit operation data plan |  |  |  |  | M | [13 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended AR to Review Data Package M: mandatory R: recommended CRR
S.TE10 | One-year in-orbit operation data report |  |  |  |  | M | [13 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
Product Assurance
S.PA1 | Product Assurance Plan | PAP |  | R | R | R | [13 empty] | ECSS-Q-ST-10C, Annex A | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA2 | Quality Assurance Plan | QAP |  | R | M | M | [13 empty] | ECSS-Q-ST-20C, Annex A | R | May be merged with S.PA1 in one single document | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA3 | Critical Item List | CIL |  | M | M | M | [13 empty] | ECSS-Q-ST-10-04C, Annex A | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA4 | Configuration Item Data List | CIDL |  | R | M | M | [13 empty] | ECSS-M-ST-40C, Annex C | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR to Review Data Package M: mandatory R: recommended MRR
S.PA5 | As-built Configuration List | ABCL |  |  | R | M | [13 empty] | ECSS-M-ST-40C, Annex D | R | To be included in S.PA26 at AR. Required at TRR only for QM, PFM or FM. | bar: Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended AR
S.PA6 | Qualification Status List | QSL |  | R | M | M | [13 empty] | ECSS-Q-ST-10C, Annex B | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.PA7 | Manufacturing and inspection flow chart |  |  | R | M | M | [13 empty] | ECSS-Q-ST-20C, Req. 5.5.1a – 5.5.1e | R | Includes MIP / KIP List (List of Inspections) | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR to Review Data Package M: mandatory R: recommended MRR
S.PA8 | Declared Materials List | DML |  | R | M | M | [13 empty] | ECSS-Q-ST-70C, Annex A | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.PA9 | Declared Mechanical Parts List | DMPL |  | R | M | M | [13 empty] | ECSS-Q-ST-70C, Annex B | R | May be merged with S.PA8 in one single document | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.PA10 | Declared Processes List | DPL |  | R | M | M | [13 empty] | ECSS-Q-ST-70C, Annex C | R | May be merged with S.PA8 in one single document | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.PA11 | Declared Components List | DCL |  | R | M | M | [13 empty] | ECSS-Q-ST-60C, Annex B | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.PA12 | Part Approval Document | PAD |  |  |  | R | [13 empty] | ECSS-Q-ST-60C, Annex D | R | PAD only required as defined in the Product Quality Requirements | bar: Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA13 | Cleanliness and contamination control plan |  |  |  | R | R | [13 empty] | ECSS-Q-ST-70-01C, Annex B | R | CCCP may not be required by the Product Quality Requirements | bar: Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA14 | Failure Mode Effects and Criticality analysis | FMECA |  | R | M | M | [13 empty] | ECSS-Q-ST-30-02C, Annex A | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA15 | Failure Detection Isolation and Recovery | FDIR |  | R | R | R | [13 empty] | ECSS-Q-ST-30C, Annex F | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA16 | Worst-Case Analysis | WCA |  | R | M | M | [13 empty] | ECSS-Q-ST-30C, Annex J | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA17 | Reliability assessment report |  |  | R | M | M | [13 empty] | ECSS-Q-ST-30C, Annex E | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA18 | Availability analysis |  |  |  | R | R | [13 empty] | ECSS-Q-ST-30-09C, Req. 6.4 | R | May be merged with S.PA17 in one single document | bar: Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA19 | Maintainability analysis |  |  |  | R | R | [13 empty] | ECSS-Q-ST-30C, Annex H | R | May be merged with S.PA17 in one single document | bar: Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA20 | Safety analysis |  |  |  | R | R | [13 empty] | ECSS-Q-ST-40C, Annex C | R | May be merged with S.PA17 in one single document | bar: Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA21 | Part stress analysis |  |  |  | M | M | [13 empty] | ECSS-Q-ST-30-11C | R | bar: Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA22 | Radiation analysis |  |  | R | M | M | [13 empty] | ECSS-Q-ST-60-15C, Annex B | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.PA23 | Request For Deviation | RFD |  |  |  | M | [13 empty] | ECSS-M-ST-40C, Annex I | R | To be delivered when raised | bar: Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR to Review Data Package M: mandatory R: recommended MRR
S.PA24 | Request For Waiver | RFW |  |  | M | M | [13 empty] | ECSS-M-ST-40C, Annex J | R | To be delivered when raised | bar: Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.PA25 | Non-Conformance Report | NCR |  |  | M | M | Review Data Package M: mandatory R: recommended MTR: M / Within 48 hours of occurrence | ECSS-Q-ST-10-09C, Annex A | R | A Non-conformance Review Board (NRB) shall be held subsequently to any NCR. The corresponding NRB report shall be delivered after NCR closure.
S.PA26 | End-Item Data Package | EIDP |  |  | R | M | [13 empty] | Part 5C, Annex | M | Template of EIDP may be released at CDR for review. | bar: Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended AR
[20 empty] | ECSS-Q-ST-20C, Annex B | R
[20 empty] | ECSS-Q-ST-20C, Annex C | R
[20 empty] | ECSS-Q-ST-20C, Annex D | R
S.PA27 | Product Data Sheet |  |  | M | M | M | [13 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended FR
S.PA28 | Single Event Phenomena Rates Calculation |  |  | R | M | M | [13 empty] | ECSS-Q-ST-60-15C, Annex B | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.PA29 | Handling, Packing, Storage, and Transportation |  |  |  | M | M | [13 empty] | Self descriptive | bar: Review Data Package M: mandatory R: recommended AR
S.PA30 | RFD / RFW List |  |  |  | M | M | [13 empty] | Self descriptive |  | Status list of all RFW / RFD | bar: Review Data Package M: mandatory R: recommended CDR to Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
Software (if applicable)
S.SW1 | Software Configuration File | SCF |  | R | R | R | [13 empty] | ECSS-M-ST-40C, Annex E | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.SW2 | Software Product Assurance Plan | SPAP |  | R | R | R | [13 empty] | ECSS-Q-ST-80C, Annex B | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR; Review Data Package M: mandatory R: recommended QR
S.SW3 | Software Requirements Specification | SRS | R | R | R | [14 empty] | ECSS-E-ST-40C, Annex D | R | bar: Review Data Package M: mandatory R: recommended MTR; Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR
S.SW4 | Software Interface Control Document | SICD |  | R | R | [14 empty] | ECSS-E-ST-40C, Annex E | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR
S.SW5 | Software Design Document | SDD | R | R | R | [14 empty] | ECSS-E-ST-40C, Annex F | R | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR
S.SW6 | Software Release Document | SrelD |  |  | R | R | [13 empty] | ECSS-E-ST-40C, Annex G | R | bar: Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.SW7 | Software User Manual | SUM |  |  | R | R | [13 empty] | ECSS-E-ST-40C, Annex H | R | bar: Review Data Package M: mandatory R: recommended CDR to Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.SW8 | Software Verification Plan | SVerP |  | R | R | [14 empty] | ECSS-E-ST-40C, Annex I | R | bar: Review Data Package M: mandatory R: recommended RR to Review Data Package M: mandatory R: recommended TRR
S.SW9 | Software Validation Plan | SValP |  | R | R | [14 empty] | ECSS-E-ST-40C, Annex J | R | bar: Review Data Package M: mandatory R: recommended RR to Review Data Package M: mandatory R: recommended TRR
S.SW10 | Software Unit or Integration Test Plan | SUITP |  | R | R | [14 empty] | ECSS-E-ST-40C, Annex K | R | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR
S.SW11 | Software Validation Specification | SVS |  |  | R | R | [13 empty] | ECSS-E-ST-40C, Annex L | R | bar: Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended EQSR to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.SW12 | Software Verification Report | SVR |  |  | R | R | [13 empty] | ECSS-E-ST-40C, Annex M | R | bar: Review Data Package M: mandatory R: recommended TRB to Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended QR
S.SW13 | Software Development Plan | SDP | R | R | R | [14 empty] | ECSS-E-ST-40C, Annex O | R | bar: Review Data Package M: mandatory R: recommended MTR to Review Data Package M: mandatory R: recommended CDR
S.SW14 | Software Configuration Management Plan |  |  | R | R | [14 empty] | ECSS-M-ST-40C, Annex A | R | bar: Review Data Package M: mandatory R: recommended RR to Review Data Package M: mandatory R: recommended CDR
S.SW15 | Software reuse file | SRF |  | R | R | R | [13 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended PDR to Review Data Package M: mandatory R: recommended CDR; Review Data Package M: mandatory R: recommended AR
[20 empty] | ECSS-E-ST-40C, Annex N | R
S.SW16 | Software license file | SLF |  |  | R | M | [13 empty] | Part 5C, Annex | M | bar: Review Data Package M: mandatory R: recommended CDR to Review Data Package M: mandatory R: recommended TRR; Review Data Package M: mandatory R: recommended AR; Review Data Package M: mandatory R: recommended PCR to Review Data Package M: mandatory R: recommended QR
(1) intended for general publication and will NOT be treated in confidence