## Objectives
Review |  | Objectives | Phase applicability M: mandatory / O: optional / Blank: excluded
Name | Acronym |  | Definition | Technology | Scylight Demonstation | Product
Mid Term Review | MTR | 1. Release of the preliminary technical requirements specification. | M
|  | 2. Preliminary concept(s) and technical solutions, including model philosophy and verification approach, to be carried forward. | M
Requirements Review | RR | 1. Release the updated technical requirements specification. |  | O
|  | 2. Assess the preliminary design definition. |  | O
|  | 3. Release the preliminary verification plan. |  | O
Preliminary Design Review | PDR | 1. Approve the technical requirements specification at all levels. |  | M |  | O
|  | 2. Verify the preliminary design of the selected concept and technical solutions against all requirements (including interfaces). |  | M |  | O
|  | 3. Close all technical trade-offs. |  | M |  | O
|  | 4. Demonstrate the feasibility of the selected concept. |  | M |  | O
|  | 5. Identify critical points and propose risk mitigation actions. |  | M |  | O
|  | 6. Release final management, engineering and product assurance plans. |  | M |  | O
|  | 7. Establish the verification plan (including draft test plans). |  | M |  | O
Critical Design Review | CDR | 1. Approve the final design. |  |  | M | M
|  | 2. Assess, through review, analysis or test results, the compliance status with the technical requirements specification (including interfaces). |  |  | M | M
|  | 3. Assess the qualification and validation status of the critical processes. |  |  | M | M
|  | 4. Release production manufacturing, assembly and testing documents. |  |  | M | M
|  | 5. Release the user manual. |  |  | M | M
|  | 6. Approve the qualification test plan. |  |  | M | M
|  | 7. Review the qualification test specification |  |  | M | M
Test Readiness Review | TRR | 1. Verify test documentation availability and suitability, including: (a) approved AITP, (b) approved test specification, (c) test predictions (when relevant), (d) test procedures (including contingency and emergency procedures), (e) test schedule, and (f) acceptance data package of lower level items (if applicable). |  | O | O | M
|  | 2. Verify that the tested item(s) is(are) built to the required standard. |  | O | O | M
|  | 4. Check that the item is in the correct test configuration. |  | O | O | M
|  | 5. Verify the acceptability of all non-conformances, waivers and deviations. |  | O | O | M
|  | 6. Confirm that test facilities and personnel are available and adequate. |  | O | O | M
Test Review Board | TRB | 1. Review the test report. |  | O | O | M
|  | 2. Examine compliance with the test specification. |  | O | O | M
|  | 3. List and examine non-conformances. |  | O | O | M
|  | 4. Assess the status of test objectives. |  | O | O | M
ScyLight Demonstration Review | SDR | 1. Confirm that the Demonstrator conforms to the contractual requirements and to an approved design configuration. |  |  | M
|  | 2. Confirm that the demonstrator is free of workmanship errors and is ready for subsequent operational use. |  |  | M
|  | 3. Verify the completeness of the Acceptance/End Item Data Package (ADP or EIDP). |  |  | M
|  | 4. Verify the acceptability of all waivers and deviations. |  |  | M
|  | 5. Confirm that the demonstrator is ready for integration with the spacecraft |  |  | M
Commissioning Results Review | CRR | 1. Review the commissioning test results relating to the performance of operational unit. |  |  | M
|  | 2. Compare the commissioning test results with the corresponding performance predictions. |  |  | M
|  | 3. Present and assess any anomaly observed during commissioning of the operational unit. |  |  | M
Phase Completion Review | PCR | 1. Present a summary of the outcome of the development phase, including conclusions and recommendations. | M | M | M | M
|  | 2. Propose an outline of future product development strategies. | M | M | M | M
|  | 3. Present the test or operational data gathered during the phase | O | M | M | M
Final Review | FR | 1. Present a summary of the outcome of the development, including conclusions and recommendations. | M | M | M | M
|  | 2. Propose an outline of future product development strategies. | M | M | M | M
|  | 3. Present the qualification test results (if no qualification review has been held previously). |  |  |  | M
|  | 4. Provide an estimation of the socioeconomic impact of the product development and of the subsequent commercialisation of the product |  |  | M | M
|  | 5. Present the operational data gathered during the first year of operation of the product. |  |  | M
|  | 6. Compare the operational data with performance predictions, including a trend analysis. |  |  | M
|  | 7. List and assess any anomaly observed during operation. |  |  | M
Qualification Review | QR | 1. Present the qualification test results (TRB objectives shall apply). |  |  |  | O
|  | 2. Confirm that the verification process has demonstrated that the design complies with the technical requirements specification. |  |  |  | O
3. Verify the acceptability of all waivers and deviations.
Manufacturing Readiness Review | MRR | 1. Review manufacturing, assembly, inspection and test documentation. |  |  | O | O
|  | 2. For flight hardware, identify differences with the qualification model (definition, fabrication, test) and evaluate the related impact. |  |  | O
|  | 3. Assess the validation status of manufacturing processes, with particular emphasis on critical processes. |  |  | O | O
|  | 4. Review the dispositions for risk reduction into the manufacturing, assembly, integration, inspection and test procedures |  |  | O | O
|  | 5. Confirm the availability of required production resources (personnel and tools) |  |  | O | O
|  | 6. Confirm the availability and compliance of parts, mechanical parts and materials. |  |  | O | O
|  | 7. Assess the cleanliness of facilities with respect to the required levels. |  |  | O | O

## Deliverables
Document |  |  | Phase applicability M: mandatory R: recommended |  |  |  | Review Data Package M: mandatory R: recommended | [15 empty] | Document definition |  | Comments
Reference | Title | Acronym | Definition | Technology | Scylight Demonstration | Product | MTR | RR | PDR | CDR | TRR | TRB | FHSR | Spacecraft Level TRR | Spacecraft Level TRB | DAR | CRR | PCR | SDRR | FR | QR | MRR | Reference | Applicability M: mandatory R: recommended
Management
S.MG1 | Project Management Plan | PMP | M | M | M | M | M | R | M | M | [9 empty] | M |  |  | Part 5A, Req. 1.1 | M
[23 empty] | ECSS-M-ST-10, Annex A | R
S.MG2 | Configuration and Documentation Management Plan | CMDP | R | R | R | R | R | R | R | [13 empty] | Part 5A, Req. 2.2 and 2.3 | M
[23 empty] | ECSS-M-ST-40, Annex A | R
S.MG3 | Risk Management Plan | RMP | R | R | R | R | R | R | R | R | [12 empty] | ECSS-M-ST-80, Annex B | R | May be merged with S.MG1 in one single document.
S.MG4 | Review Procedure |  | R | R | R | R | R / At each review | [15 empty] | ECSS-M-ST-10-01, Annex A | R
S.MG5 | Business Potential | BP | M | M | M | M | M | R | M | M |  |  | M |  |  | M | M | M |  | M | R |  | Part 2 | M
S.MG6 | Monthly Progress Report | MPR | M | M | M | M | M / Monthly | [15 empty] | Template in hyperlink | M | Also see Part 5A, Req. 3.1 – 3.3
S.MG7 | Schedule Bar Chart | SBC | M | M | M | M | M / Monthly and at each progress meeting | [15 empty] | Part 5B, Req. 3.3 and 5.6 | M | May be merged with S.MG6 in one single document.
[23 empty] | ECSS-M-ST-60, Annex B. | R
S.MG8 | Minutes of Meeting | MoM | M | M | M | M | M / For each review or meeting | [15 empty] | Part 5A, Req. 3.2 and 3.3 | M
S.MG9 | Risk Register | RR | M | M | M | M | M / Monthly and at each progress meeting | [15 empty] | ECSS-M-ST-80C, Annex D | R
S.MG10 | Document List | DL | M | M | M | M | M | R | M | M | M | M | M | M | M | M | M | M |  | M | R | R | Self descriptive |  | List of all documents produced in the frame of the contract
S.MG11 | Final Report(1) | FR | M | M | M | M | [11 empty] | M |  | M |  |  | Part 5C, Annex | M
S.MG12 | Final Data Package | FDP | M | M | M | M | [11 empty] | M |  | M |  |  | Part 5C, Annex | M
S.MG13 | Justification for non-continuation |  | M | M | M | [14 empty] | M |  |  | Part 5C, Req. 4.8 and 4.9 | M | If applicable.
S.MG14 | Project Web Page(1) | PWP | M | M | M | M | M | R | M | M | M | M | R |  |  | M | M | M |  | M | R | R | Template in hyperlink | M | Also see Part 5A, Req. 3.5 – 3.8
S.MG15 | High resolution image(1) |  | M | M | M | M | [6 empty] | M |  |  | M |  | M |  | M |  |  | Part 5C, Annex | M | Shall be delivered for each Development Phase during the last milestone review meeting of that Phase.
S.MG16 | Activity Summary Description(1) | ASD | M | M | M | M | [11 empty] | M |  | M |  |  | Part 5C, Annex | M | Shall be delivered for each Development Phase during the last milestone review meeting of that Phase.
S.MG17 | Socio-economic Impact Questionnaire | SIQ |  |  | M | M | [13 empty] | M |  |  | Part 5C, Annex | M | Template in hyperlink
S.MG18 | Contract Inventory |  | M | M | M | M | [6 empty] | M |  |  | M |  | M |  | M |  |  | ECSS-M-ST-60, Annex I | R | List of all items produced under the Contract with an individual or batch value exceeding 10k€.
S.MG19 | Schedule for follow-on Phase(s) |  | M | M | M | M | [11 empty] | M
S.MG20 | Review and Deliverable Plan for follow-on Phase(s) |  | M | M | M | M | [11 empty] | M
S.MG21 | Costings for follow-on phase(s) |  | M | M | M | M | [11 empty] | M
Engineering
S.EN1 | Design, Development and Verification Plan / Product Development Plan |  | M | M | M | M | M | R | M | M |  |  | R |  |  |  |  | M |  | M | R |  | Parts 3B and 3C | M
S.EN2 | Technical Requirements Specification / Product Specification |  | M | M | M | M | M | R | M | M | M |  | M |  |  | M |  |  |  |  | M |  | Part 3A | M | For lower levels as well, if applicable.
[23 empty] | ECSS-E-ST-10-06, Annex A | R
S.EN3 | Requirements Traceability Matrix | RTM | R | R | M | M | R | R | R | M | [10 empty] | R |  | ECSS-E-ST-10, Annex N | R | If applicable. May be merged with S.EN2 in one single document.
S.EN4 | Verification Control Document | VCD | R | R | R | R | R |  | R | R |  |  | R |  |  | R | R |  |  |  | R |  | ECSS-E-ST-10-02, Annex B | R
S.EN11 | Compliance Matrix to Technical Specification |  |  | M | M | M |  |  | M | M |  |  | M |  |  | M |  |  |  |  | M |  | Self descriptive |  | May be merged with S.EN2 in one single document.
S.EN12 | Design Verification Compliance Matrix | DVCM |  | M | M | M |  |  | M | M |  |  | M |  |  | M |  |  |  |  | R |  | ECSS-E-ST-10-02, Annex B | R | May be merged with S.EN2 in one single document.
S.EN13 | Specification tree |  | R | R | R | R | R | R | R | R | [12 empty] | ECSS-E-ST-10, Annex J | R | If applicable.
S.EN14 | Design Definition File | DDF | R | M | M | M | R | R | M | M | [10 empty] | R |  | ECSS-E-ST-10, Annex G | R
S.EN15 | Design Justification File | DJF | R | M | M | M | R | R | M | M | [10 empty] | R |  | ECSS-E-ST-10, Annex K | R
S.EN16 | Part drawings |  |  | R | R | M |  |  | R | M | [10 empty] | R | R | Self descriptive | R | May be available for on-site review only.
S.EN17 | Assembly drawings |  |  | R | R | M |  |  | R | M |  |  | R |  |  | R |  |  |  |  | R | R | Self descriptive | R | May be available for on-site review only.
S.EN18 | Interface Control Document | ICD |  | R | M | M |  | R | M | M |  |  | M |  |  | M |  |  |  |  | R | R | ECSS-E-ST-10-24, Annex C | R
S.EN19 | User Manual | UM |  |  | M | R |  |  |  | R |  |  | M |  |  | M |  |  |  |  | R |  | ECSS-E-ST-10, Annex P | R
S.EN20 | Trade-Off Report | TOR | R | R | R |  | R | R | R | [13 empty] | ECSS-E-ST-10, Annex L | R | If applicable
S.EN21 | Performance Analyses |  | R | R | R | M | R | R | M | M | [10 empty] | R |  | ECSS-E-ST-10, Annex Q | R | For instance: worst-case performance, power budget, leakage, gauging, sloshing, motorization, kinematics. May be merged with S.EN9 in one single document.
S.EN22 | Environmental Analyses |  |  | R | R | M |  | R | M | M | [10 empty] | R |  | ECSS-E-ST-10, Annex Q | R | For instance: thermal, mechanical, thermo-elastic, fatigue, fracture, EMC, ESD, venting, plume effects, corona. May be merged with S.EN7 in one single document.
S.EN17 | Mathematical Models |  |  |  | R | R |  |  |  | R | [10 empty] | R |  | ECSS-E-ST-31, Annex B for thermal | R | E.g. performance, thermal, mechanical.
[23 empty] | ECSS-E-ST-32, Annex A for CAD | R
[23 empty] | ECSS-E-ST-32, Annex I for mechanical | R
[23 empty] | ECSS-E-ST-35 Annex I for propulsion | R
[23 empty] | ECSS-E-ST-60-20, Annex A for star sensor | R
S.EN18 | Satellite level accommodation report |  |  |  | M | [7 empty] | M |  |  | M | [6 empty] | Self descriptive | R | For instance: accommodation studies, design modifications performed to accommodate the innovative product, any hardware specifically required for accommodation purposes and satellite level AIT, specific activities related to the innovative product during the AIT and launch campaigns.
S.EN19 | Technical Description |  | M | M | M | M |  | M | M | M |  |  | R |  |  | R |  |  |  |  | M |  | Self descriptive
S.EN20 | Statement of compliance to the Specifications |  | R | R | M | M |  |  | R | M |  |  | M |  |  | M | [6 empty] | Self descriptive |  | Applicable only if multiple specifications are used
S.EN21 | Mass Budget |  |  |  | M | M |  |  | R | M |  |  | M |  |  | M |  |  |  |  | M |  | ECSS-E-ST-10, Annex Q | M
Testing
S.TE1 | Assembly, Integration and Test Plan | AITP |  | R | R | R |  |  | R | R | R |  |  | R | [6 empty] | R |  | ECSS-E-ST-10-03, Annex A | R
S.TE2 | Test Specification | TSPE |  | M | R | M |  |  | M | M | M |  |  | M | [8 empty] | ECSS-E-ST-10-03, Annex B | R | These documents are required for Engineering Model testing, as well as for qualification and acceptance tests. Test procedures may be available for on-site review only.
S.TE3 | Test Procedure | TPRO |  | R | R | M |  |  | R | M | M |  |  | M | [6 empty] | M |  | ECSS-E-ST-10-03, Annex C | R
S.TE4 | Test Report | TRPT |  | M | M | M | [5 empty] | M |  |  | M |  |  | M |  | M | M |  | ECSS-E-ST-10-02, Annex C | R
S.TE5 | AIT report | AITR |  |  | R | R | [5 empty] | R |  |  | R | [7 empty] | ECSS-E-ST-10-02, Annex C | R
S.TE6 | Satellite AIT report |  |  |  | M | [8 empty] | M |  | M | [6 empty] | Part 5C, Annex | M
S.TE7 | In-Orbit Test plan |  |  |  | M | [7 empty] | M |  |  | M | [6 empty] | Part 5C, Annex | M
S.TE8 | IOT report |  |  |  | M | [11 empty] | M | [5 empty] | Part 5C, Annex | M
S.TE9 | One-year in-orbit operation test plan |  |  |  | M | [7 empty] | M |  |  | M | M | [5 empty] | Part 5C, Annex | M
S.TE10 | One-year in-orbit operation test report |  |  |  | M | [12 empty] | R |  | M |  |  | Part 5C, Annex | M
Product Assurance
S.PA1 | Product Assurance Plan / Quality Plan | PAP |  | R | R | R |  |  | R | R | [10 empty] | R |  | ECSS-Q-ST-10, Annex A | R
S.PA2 | Quality Assurance Plan | QAP |  | R | M | M |  |  | R | M | [10 empty] | R |  | ECSS-Q-ST-20, Annex A | R | May be merged with S.PA1 in one single document
S.PA3 | Critical Item List | CIL |  | M | M | M |  |  | M | M | [10 empty] | R |  | ECSS-Q-ST-10-04, Annex A | R
S.PA4 | Configuration Item Data List | CIDL |  | R | M | M |  |  | R | M | R |  | M |  |  | M |  |  |  |  | R | R | ECSS-M-ST-40, Annex C | R
S.PA5 | As-built Configuration List | ABCL |  |  | M | R |  |  |  |  | M |  | M |  |  | M | [6 empty] | ECSS-M-ST-40, Annex D | R | To be included in S.PA26 at AR. Required at TRR only for QM, PFM or FM.
S.PA6 | Qualification Status List | QSL |  | R | M | M |  |  | R | M | M |  | M |  |  | M |  |  |  |  | R |  | ECSS-Q-ST-10, Annex B | R
S.PA7 | Manufacturing and inspection flow chart |  |  | R | M | M |  |  | R | M |  |  | M |  |  | M |  |  |  |  | R | R | ECSS-Q-ST-20, Req. 5.5.1a – 5.5.1e | R | Includes MIP / KIP List (List of Inspections)
S.PA8 | Declared Materials List | DML |  | R | M | M |  |  | R | M |  |  | M |  |  | M |  |  |  |  | R |  | ECSS-Q-ST-70, Annex A | R
S.PA9 | Declared Mechanical Parts List | DMPL |  | R | M | M |  |  | R | M |  |  | M |  |  | M |  |  |  |  | R |  | ECSS-Q-ST-70, Annex B | R | May be merged with S.PA8 in one single document
S.PA10 | Declared Processes List | DPL |  | R | M | M |  |  | R | M |  |  | M |  |  | M |  |  |  |  | R |  | ECSS-Q-ST-70, Annex C | R | May be merged with S.PA8 in one single document
S.PA11 | Declared Components List | DCL |  | R | M | M |  |  | R | M |  |  | M |  |  | M |  |  |  |  | R |  | ECSS-Q-ST-60, Annex B | R
S.PA12 | Part Approval Document | PAD |  |  | R |  |  |  |  | R | [10 empty] | R |  | ECSS-Q-ST-60, Annex D | R | PAD only required as defined in the Product Quality Requirements
S.PA13 | Cleanliness and contamination control plan |  |  |  | R | R |  |  |  | R | [10 empty] | R |  | ECSS-Q-ST-70-01, Annex B | R | CCCP may not be required by the Product Quality Requirements
S.PA14 | Failure Mode Effects and Criticality analysis | FMECA |  | R | M | M |  |  | R | M | [10 empty] | R |  | ECSS-Q-ST-30-02, Annex A | R
S.PA15 | Failure Detection Isolation and Recovery | FDIR |  | R | R | R |  |  | R | R | [10 empty] | R |  | ECSS-Q-ST-30, Annex F | R
S.PA16 | Worst-Case Analysis | WCA |  | R | M | M |  |  | R | M | [10 empty] | R |  | ECSS-Q-ST-30, Annex J | R
S.PA17 | Reliability assessment report |  |  | R | M | M |  |  | R | M | [10 empty] | R |  | ECSS-Q-ST-30, Annex E | R
S.PA18 | Availability analysis |  |  |  | R | R |  |  |  | R | [10 empty] | R |  | ECSS-Q-ST-30-09, Req. 6.4 | R | May be merged with S.PA17 in one single document
S.PA19 | Maintainability analysis |  |  |  | R | R |  |  |  | R | [10 empty] | R |  | ECSS-Q-ST-30, Annex H | R | May be merged with S.PA17 in one single document
S.PA20 | Safety analysis |  |  |  | R | R |  |  |  | R | [10 empty] | R |  | ECSS-Q-ST-40, Annex C | R | May be merged with S.PA17 in one single document
S.PA21 | Part stress analysis |  |  |  | M | M |  |  |  | M | [10 empty] | R |  | ECSS-Q-ST-30-11 | R
S.PA22 | Radiation analysis |  |  | R | M | M |  |  | R | M | [10 empty] | R |  | ECSS-Q-ST-60-15, Annex B | R
S.PA23 | Request For Deviation | RFD |  |  | M | [7 empty] | M | R | R | M |  |  |  |  | R | R | ECSS-M-ST-40, Annex I | R | To be delivered when raised
S.PA24 | Request For Waiver | RFW |  |  | M | M |  |  |  |  | M |  | M | R | R | M |  |  |  |  | M |  | ECSS-M-ST-40, Annex J | R | To be delivered when raised
S.PA25 | Non-Conformance Report | NCR |  |  | M | M | M / Within 48 hours of occurrence | [15 empty] | ECSS-Q-ST-10-09, Annex A | R | A Non-conformance Review Board (NRB) shall be held subsequently to any NCR. The ccoresponding NRB report shall be delivered after NCR closure
S.PA26 | End-Item Data Package | EIDP |  |  | M | R |  |  |  | R |  |  | M |  |  | M | [6 empty] | Part 5C, Annex | M | Template of EIDP may be released at CDR for review.
[23 empty] | ECSS-Q-ST-20, Annex B | R
[23 empty] | ECSS-Q-ST-20, Annex C | R
[23 empty] | ECSS-Q-ST-20, Annex D | R
S.PA27 | Product Data Sheet |  |  | M | M | M | [6 empty] | M |  |  | M |  | M |  | M |  |  | Part 5C, Annex | M
S.PA28 | Single Event Phenomena Rates Calculation |  |  | R | M | M |  |  | R | M | [10 empty] | M |  | ECSS-Q-ST-60-15, Annex B | R
S.PA29 | Handling, Packing, Storage, and Transportation |  |  |  | M | M | [6 empty] | M |  |  | M | [6 empty] | Self descriptive
S.PA30 | RFD / RFW List |  |  |  | M | M |  |  |  | M | M |  | M | M | M | M |  |  |  |  | M |  | Self descriptive |  | Status list of all FRW / RFD
Software (if applicable)
S.SW1 | Software Configuration File | SCF |  | R | R | R |  |  | R | R | R |  | R |  |  | R |  |  |  |  | R |  | ECSS-M-ST-40, Annex E | R
S.SW2 | Software Product Assurance Plan | SPAP |  | R | R | R |  |  | R | R | [10 empty] | R |  | ECSS-Q-ST-80, Annex B | R
S.SW3 | Software Requirements Specification | SRS | R | R | R | R | R |  | R | R | [12 empty] | ECSS-E-ST-40, Annex D | R
S.SW4 | Software Interface Control Document | SICD |  | R | R | R |  |  | R | R | [12 empty] | ECSS-E-ST-40, Annex E | R
S.SW5 | Software Design Document | SDD | R | R | R | R | R | R | R | R | [12 empty] | ECSS-E-ST-40, Annex F | R
S.SW6 | Software Release Document | SrelD |  |  | R | R |  |  |  |  | R |  | R | R | R | R |  |  |  |  | R |  | ECSS-E-ST-40, Annex G | R
S.SW7 | Software User Manual | SUM |  |  | R | R |  |  |  | R | R |  | R | R | R | R |  |  |  |  | R |  | ECSS-E-ST-40, Annex H | R
S.SW8 | Software Verification Plan | SVerP |  | R | R | R |  | R | R | R | R |  |  | R | [8 empty] | ECSS-E-ST-40, Annex I | R
S.SW9 | Software Validation Plan | SValP |  | R | R | R |  | R | R | R | R |  |  | R | [8 empty] | ECSS-E-ST-40, Annex J | R
S.SW10 | Software Unit or Integration Test Plan | SUITP |  | R | R | R |  |  | R | R | [12 empty] | ECSS-E-ST-40, Annex K | R
S.SW11 | Software Validation Specification | SVS |  |  | R | R |  |  |  | R | [10 empty] | R |  | ECSS-E-ST-40, Annex L | R
S.SW12 | Software Verification Report | SVR |  |  | R | R | [5 empty] | R | R |  | R | R |  |  |  |  | R |  | ECSS-E-ST-40, Annex M | R
S.SW13 | Software Development Plan | SDP | R | R | R | R | R | R | R | R | [12 empty] | ECSS-E-ST-40, Annex O | R
S.SW14 | Software Configuration Management Plan |  |  | R | R | R |  | R | R | R | [12 empty] | ECSS-M-ST-40, Annex A | R
S.SW15 | Software reuse file | SRF |  | R | R | R |  |  | R | R |  |  | R |  |  | R | [6 empty] | Part 5C, Annex | M
[23 empty] | ECSS-E-ST-40, Annex N | R
S.SW16 | Software license file | SLF |  |  | M | R |  |  |  | R | R |  | M |  |  | M |  | M |  | M | R |  | Part 5C, Annex | M
(1) intended for general publication and will NOT be treated in confidence